## LFS Redesign Analysis

(notes from Room 3 Dec 18,19t)

# LFS work orders for 2002 sustaining

10 core modules – web & print

3 discretionary modules – web & print

6 supporting pieces – print only

- Modules updates are done internally for print; for web, the content is coded by Ideas interactive and then uploaded through Dave Carlson.

Bulletin Board –

- being developed by Webfeat

- to be launched end of December 2001-12-19 web based tool helping learners with the transition of lending modules into Sales & Service segment

- also will provide info on latest updates made to modules and CMTs

- help to announce new modules, tools from LFS

Infolink –

- updates done through Webfeat

CMT-

- updates done internally.

Chris Bruce to provide Joanne with overview of financials; copy of presentation originally done for Peter Tate to be shared also.

We discussed potential of needing to re-prioritize work orders upon confirmation of re-design plans, capacity , and funding review.

RIDR – Retail Investment Delivery Re-Design

- investment curriculum, processes, product, technology, and people within scope of this initiative.

- Joanne to follow up with Tracy McClure to get more info.

### Branch Network Re-Organization

- Copy of presentation received and reviewed

- Some concern that we are not “at the table” in a significant way on this project.

- Need to link in with April Taggart and/or Sue Croft in January.

- Need to get updates on pilot.

- What is communication strategy? Search on BMO central and OneSource does not reflect any corporate communications or plans, etc.

- Want to get copy of job aid / managers guide that has apparently been developed to assist with transition.

- Project timeline reflects education/training development taking place at same time as  first phase of National rollout – Q2 2002.

Frank’s framework for re-design planning (in random order)

# Stakeholders

- Senior leadership

- BSO

- HR

- LOB

- IFL

- Branch and end-users / performers

# Content & Validation

- SMEs

- High performers

- Sign-off authority

# Work Order Process

- Need identification & analysis

- Allocation of resources

# Program Objectives

- Strategic

- Divisional

- Individual / team

Target Audience  (Chris Bruce getting some of this info)

- Age

- Gender

- Work experience

- Education

- Motivation

- Number and location

# Transfer of Learning (or Performance Delivery)

- Participants

- Design

- Content

- Organizational context

# Assessment & Evaluation

- Accreditation ?

- Recognition of achievement

- Training Days

# START Program

- Need to validate or determine need for on-going work for START.

#### Discussion paper on Accreditation

- Begin to collect data to present the current state ( Chris Bruce & Anne Brown); future state or alternatives to current state ( Frank); Background and academic perspective on accreditation as a means of qualification ( Joanne).

- Paper is intended to take a position on alternatives and make recommendations relative to ownership as well.

- Draft of paper to be prepared by January 9th.

- January 9th – meet to discuss and prepare recommendations.

LFS Team Meeting – January 3rd. Joanne facilitating discussion with Sam.

# Pathway Connect – SBB & Retail

- Overview of SBB learning plans corresponding to PathwayConnect implementation received and reviewed.

- Plans for retail learning pending – Joanne following up.