A Vancouver based company is preparing for the release of the next version of its’ software.  As with previous versions of their product, they are planning the technical development activities, marketing, communication, pricing, implementation and training that will be required for the launch.

The head office for the company is in Vancouver, however there are sales offices located in San Francisco, Chicago and New York.  The company has experienced considerable growth for the past 3 years, predominantly in North America. There are approximately 180 clients in the U.S. and 45 in Canada.

In the last year, they have established global strategic partners who sell and provide after sales service for the product  - these partners are located in London, Stockholm, Sydney and Hong Kong.  Partnerships in Tokyo, Frankfurt and Dublin are close to completion.  These partners will be jointly responsible for the roll-out of the new version to the international client group.  The sales team is focussed on international partnership opportunities and expanding North American client base.  New clients who are signed and ready to use application by March 1st, will be put on new version immediately.

The R&D team confirms that the interface design will be complete by November 15th, with a functional version to be complete on January 31st; followed by QA and user acceptance testing to be done by February 20th.  The application will be ready for beta testing March 1st.  The date to have all clients on the new platform is April 30th.

All teams involved with the new product launch are going to have to deliver to extremely tight deadlines with only minimal new resources, as the company needs to keep expenses flat in order to satisfy ROI forecasts.  The client base has been growing, but the company is not yet profitable after 6 years in operation and investors are not willing to increase capital exposure.

The Learning team is facing a significant challenge for the launch too.  There are 3 fulltime trainers who do training at the client site, or via webex or placeware.  Facilitated training sessions are well received by clients and achieve learning objectives.  Trainers work closely with the product group and although are not subject matter experts, are required to have strong working knowledge of the application to design and deliver the learning.  On-site training for current version of software is one full day; remote sessions are 3 to 4 hours.  The new version has 5 key new functions.

______________________________________________________________________________

Identify several challenges that the learning team will have to overcome in order to support the new product launch.

Create a proposal for the LOB executive and project team outlining the learning plan you feel will best meet the needs of the company.