## Sheet1
Learning for Success- |  | Q4 2002 and F 2003
September | October | November | December | January | February | March | April | Q3 | Q4
LFS Redesign <LFS-R>
Learning for Success- September: ~content review;.; Q4 2002 and F 2003 November: ~monthly updates; Q4 2002 and F 2003 February: ~site/learning evaluation design/development | ~learning evaluation launch
~selected new content developed |  | ~content re-design continues
~site QA |  | ~continue marketing LFS-R
~site launch Oct 31
LFS "old"
~content lockdown Sep 1 |  | ~takedown out of date modules |  |  | ~communication of Apr 30 site take down
~no updates to modules. |  | ~redirect to LFS-R for updated modules |  |  | ~more emphasis on redirect to LFS-R
~all modules still posted
~redirect to LFS-R for updated modules
CMTs
~continuation of Phoenix platform |  |  |  |  | ~communication conversion to new tests
~gather requirements for future LFS testing |  |  |  |  | ~prep of takedown of Phoenix platform
~minimal maintenance
CMT Redesign <CMT-R>
Q4 2002 and F 2003 December: ~finalize requirements from LOB & Performance Mgmt | ~new testing structure launch.
~design/development of testing architecture <database enhancements>
~create tests aligned with LFS-R structure <content & role specific>
~ preparation for April 30 launch on LFS-R.
Redesign Team |  | LFS Team
~final stages of design/dev |  | ~ LFS owners take over
~prep for launch
~hand-off to LFS Team
DRAFT plan created by J. Brown, Aug 19/2002.